## Sheet1
Carrier Technology Ltd. — Enterprise Risk Register
Risk ID | Risk Category | Risk Description | Inherent Impact (1-5) | Inherent Likelihood (1-5) | Inherent Risk Score | Existing Controls & Safeguards | Residual Risk Level | Risk Strategy | Mitigating Action Plan | Risk Owner | Key Risk Indicator (KRI)
RSK-2026-01 | Cyber & Infrastructure | Compromise of production cloud environment via dormant or over-privileged employee credentials. | 5 | 4 | 20 (High) | Quarterly manual user access reviews (UAR). | Medium | Mitigate | Integrate Okta IdP with AWS via SCIM for automated provisioning/deprovisioning within 24 hours of HR offboarding. | Head of IT / SecOps | % of offboarding tickets closed within 24 hours (Target: 100%).
RSK-2026-02 | Third-Party / Vendor | Data breach originating from critical SaaS vendor/subprocessor handling confidential customer data. | 4 | 4 | 16 (High) | Standard Non-Disclosure Agreements (NDAs); ad-hoc security reviews. | Meduim | Mitigate | Mandate Vendor Risk Management (VRM) security reviews & SOC 2 Type II collection prior to contract execution. | GRC Lead / Procurement | % of Tier-1 vendors with validated SOC 2 / ISO certifications (Target: 100%).
RSK-2026-03 | Compliance & Regulatory | Non-compliance with global privacy laws (GDPR/CCPA) due to unencrypted backup storage buckets. | 4 | 3 | 12 (Medium) | Main production database is encrypted at rest using AWS KMS. | Low | Mitigate | Deploy cloud infrastructure guardrails (AWS SCPs) to enforce KMS encryption on all backup S3 buckets. | Cloud Infrastructure Lead | Number of unencrypted storage buckets detected in daily scans (Target: 0).
RSK-2026-04 | Operational / Security | Exploitation of known critical vulnerabilities (CVEs) on production servers due to delayed patching. | 4 | 4 | 16 (High) | Monthly vulnerability scanning using automated scanning tools. | Medium | Mitigate | Build automated patch deployment pipeline with automated regression tests to meet 14-day patching SLA. | DevOps Manager | Average Mean Time to Patch (MTTP) for Critical CVEs (Target: ≤ 14 days).
RSK-2026-05 | Business Continuity | Extended service outage and customer SLA breach due to untested Disaster Recovery (DR) procedures. | 5 | 2 | 10 (Medium) | Documented Disaster Recovery Plan (DRP) and backup schedules. | Low | Mitigate | Update architecture diagrams and conduct mandatory annual tabletop exercise and simulated failover test. | BCDR Coordinator / VP Ops | Days elapsed since last DR tabletop exercise (Target: ≤ 365 days).
Risk Scoring Key:
Inherent Risk Score = Impact (1–5) × Likelihood (1–5) [Max = 25].
Scores 15–25: High Risk ¦ Scores 8–14: Medium Risk ¦ Scores 1–7: Low Risk.
Residual Risk: The remaining risk level after existing controls and mitigation plans are factored in.