## Sheet1
Carrier Technology Ltd. — Vendor Security Remediation Tracker
Vendor ID | Vendor Name | Service Provided | Data Sensitivity / Classification | Initial Risk Rating | Identified Security Deficiency / Audit Gap | Required Remediation Action | ISO 27001 Mapping | Target Remediation SLA | Current Status | Remediation Owner | Next Review Date
VND-2026-01 | CloudData Analytics | Customer Data Processing & ETL | Restricted (PII / Financial) | High | Missing current SOC 2 Type II report; outdated penetration testing report (>18 months old). | Obtain updated SOC 2 Type II report; execute DPA with revised breach notification window (24 hrs). | A.5.19, A.5.21 | 30 Days | In Progress | GRC Analyst / Procurement | 2026-11-05
VND-2026-02 | PayGate Corp | Payment Gateway Integration | Restricted (PCI-DSS Data) | Critical | SOC 2 report highlighted exception in quarterly privilege access review; no SOC 1 available. | Require Vendor Bridge Letter; obtain PCI-DSS Attestation of Compliance (AoC) and proof of access remediation. | A.5.19, A.8.2 | 14 Days | Under Review | SecOps Lead / Vendor Manager | 2026-10-19
VND-2026-03 | WorkForce SSO | Identity & Access Management | Restricted (User Credentials) | Critical | Lack of mandatory MFA enforcement for administrative access to tenant management console. | Enforce MFA via tenant settings; verify IP whitelisting configuration for administrative endpoints. | A.5.15, A.8.2 | 14 Days | Remediated | IAM Specialist / IT | 2027-01-15
VND-2026-04 | SupportDesk SaaS | Customer Ticketing & Support | Confidential (Customer Support Logs) | Medium | Completed Vendor Security Questionnaire SIG Lite) indicates lack of data encryption at rest on secondary backups. | Mandate cloud backup encryption via contractual amendment; collect formal sign-off from vendor CISO. | A.8.24, A.5.19 | 60 Days | Pending Vendor | GRC Lead | 2026-11-30
VND-2026-01 | CodePipeline Inc | DevOps CI/CD SaaS Pipeline | Confidential (Source Code / IP) | High | Vendor subprocessor list not disclosed or maintained; no contractual right-to-audit clause in place. | Negotiate updated Master Services Agreement (MSA) adding subprocessor notification SLA and audit rights. | A.5.21, A.5.19 | 45 Days | In Negotiation | Legal / Procurement | 2026-12-01